## Gantt chart
Co-expression of cerebral palsy risk genes in the developing human brain: project timeline
Project start (Monday of week 1) |  | 2026-10-05 | Yellow cell: change this date and every date and bar moves with it.
Current week |  | 1
Progress |  | 0 of 33 tasks done
Key |  | Planned | In progress | Done | Delayed | Milestone | Current week
ID | Phase | Task | Owner | Start week | End week | Start date | End date | Status | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5 | Wk 6 | Wk 7 | Wk 8
[8 empty] | Week number | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
[8 empty] | Week starting | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23
1 | 1. Set-up and protocol | Email protocol, title and eligibility criteria to supervisor | Me | 1 | 1 | 2026-10-05 | 2026-10-11 | Not started | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | 1. Set-up and protocol | Agree second screener and screening proportion | Me + supervisor | 1 | 1 | 2026-10-05 | 2026-10-11 | Not started | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | 1. Set-up and protocol | Confirm access to Embase and Web of Science or Scopus | Me | 1 | 1 | 2026-10-05 | 2026-10-11 | Not started | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | 1. Set-up and protocol | Get Jin 2020 full text and check for a brain expression analysis | Me | 1 | 1 | 2026-10-05 | 2026-10-11 | Not started | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | 1. Set-up and protocol | Check search strings with supervisor or librarian | Me + supervisor | 1 | 1 | 2026-10-05 | 2026-10-11 | Not started | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | 1. Set-up and protocol | MILESTONE: protocol registered on OSF | Me | 1 | 1 | 2026-10-05 | 2026-10-11 | Not started | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | 1. Set-up and protocol | Set up Rayyan, Zotero, R and RStudio, and search alerts | Me | 1 | 1 | 2026-10-05 | 2026-10-11 | Not started | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | 1. Set-up and protocol | Core reading (14-day reading plan) | Me | 1 | 2 | 2026-10-05 | 2026-10-18 | Not started | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
9 | 2. Searching and screening | Run all searches on one day and complete the search log | Me | 2 | 2 | 2026-10-12 | 2026-10-18 | Not started | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
10 | 2. Searching and screening | Import records to Rayyan and remove duplicates | Me | 2 | 2 | 2026-10-12 | 2026-10-18 | Not started | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
11 | 2. Searching and screening | Pilot screening of 50 records with second screener | Me + second screener | 2 | 2 | 2026-10-12 | 2026-10-18 | Not started | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0
12 | 2. Searching and screening | Title and abstract screening, Search B (gap) | Me + second screener | 2 | 3 | 2026-10-12 | 2026-10-25 | Not started | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0
13 | 2. Searching and screening | Title and abstract screening, Search A (genes) | Me + second screener | 2 | 3 | 2026-10-12 | 2026-10-25 | Not started | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0
14 | 2. Searching and screening | Full-text screening, Searches A and B | Me + second screener | 3 | 3 | 2026-10-19 | 2026-10-25 | Not started | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
15 | 2. Searching and screening | Citation chasing and registry checks | Me | 3 | 3 | 2026-10-19 | 2026-10-25 | Not started | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0
16 | 3. Extraction | Extract gene data from main texts and supplements | Me | 3 | 4 | 2026-10-19 | 2026-11-01 | Not started | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0
17 | 3. Extraction | Assign gene evidence tiers (ClinGen, Gene2Phenotype) | Me | 4 | 4 | 2026-10-26 | 2026-11-01 | Not started | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
18 | 3. Extraction | Complete gap table (criteria A, B, C) | Me + second screener | 4 | 4 | 2026-10-26 | 2026-11-01 | Not started | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
19 | 3. Extraction | Draw PRISMA flow diagrams | Me | 4 | 4 | 2026-10-26 | 2026-11-01 | Not started | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
20 | 3. Extraction | MILESTONE: gap confirmed and Tier 1 gene list final | Me + supervisor | 4 | 4 | 2026-10-26 | 2026-11-01 | Not started | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
21 | 4. Analysis | Practise WGCNA on a small BrainSpan subset | Me | 3 | 4 | 2026-10-19 | 2026-11-01 | Not started | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0
22 | 4. Analysis | Download and prepare BrainSpan data | Me | 5 | 5 | 2026-11-02 | 2026-11-08 | Not started | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
23 | 4. Analysis | Build co-expression networks and test CP gene enrichment | Me | 5 | 5 | 2026-11-02 | 2026-11-08 | Not started | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
24 | 4. Analysis | Map CP modules to brain regions and developmental periods | Me | 5 | 6 | 2026-11-02 | 2026-11-15 | Not started | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0
25 | 4. Analysis | Cell-type enrichment using developing-brain single-cell data | Me | 6 | 6 | 2026-11-09 | 2026-11-15 | Not started | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
26 | 4. Analysis | Specificity comparison (SFARI, Gene2Phenotype) and robustness checks | Me | 6 | 6 | 2026-11-09 | 2026-11-15 | Not started | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
27 | 4. Analysis | Exploratory: genes from children with and without perinatal risk factors | Me | 6 | 6 | 2026-11-09 | 2026-11-15 | Not started | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0
28 | 5. Writing and preprint | Draft methods and results with figures | Me | 7 | 7 | 2026-11-16 | 2026-11-22 | Not started | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
29 | 5. Writing and preprint | Draft introduction and discussion | Me | 7 | 7 | 2026-11-16 | 2026-11-22 | Not started | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0
30 | 5. Writing and preprint | Supervisor review and revisions | Me + supervisor | 8 | 8 | 2026-11-23 | 2026-11-29 | Not started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
31 | 5. Writing and preprint | Update searches; complete PRISMA checklist | Me | 8 | 8 | 2026-11-23 | 2026-11-29 | Not started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
32 | 5. Writing and preprint | Upload code to GitHub and Zenodo | Me | 8 | 8 | 2026-11-23 | 2026-11-29 | Not started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
33 | 5. Writing and preprint | MILESTONE: preprint posted (bioRxiv or medRxiv) | Me | 8 | 8 | 2026-11-23 | 2026-11-29 | Not started | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
How to use: set Status in column I from the dropdown. Change Start week or End week (blue) to move a bar. Bars colour by status; the current week is shaded.
Formulas:
Milestone = C2+([Done]-1)*7
Current week = C2+([Delayed]-1)*7+6