## About
Site Start-Up & Essential Document Tracker (sample)
FICTIONAL DATA ONLY. The study, sites, people and figures are invented for demonstration. No real trial, site or patient information.
Purpose
Shows how a Clinical Trial Coordinator could track essential documents, site readiness, follow-up actions and site payments for a UK study with five sites.
Tabs
Dashboard - summary counts, per-site view and charts, all calculated from the other tabs
Settings - report date, warning windows and drop-down lists
Sites - one row per site: target vs actual Site Ready date, % documents filed, Site Ready blockers
Gantt - start-up phases per site on a weekly timeline: planned against actual, with status and days vs plan
Documents - one row per essential document per site: status, expiry flag, filing quality check, next action and chase date
Payments - milestone payments per site: budget vs invoiced, days outstanding
Contact Log - record of contact with sites and whether follow-ups are done
Change Log - audit trail: what was changed, when, by whom and why
How to use
Blue text = cells you type into. Black text = formulas; do not overwrite.
Change the Report date on Settings and every flag, count and days-outstanding figure updates.
Status columns use drop-down lists so entries stay consistent and the counts stay accurate.
Enter a Chase date only while an action is open; clear it when the action is complete.
Record every change to a status, date or amount on the Change Log tab.
Flags
Document flag: Expired / Missing (red), Expiring soon (amber), In progress (grey), OK (green).
Chase status: Overdue (red), Due this week (amber), Scheduled (grey).
Filing QC: Pass if filed within the filing target after receipt, otherwise Late.

## Dashboard
Study DEMO-001: start-up dashboard (fictional data)
Report date | 2026-10-09
Document flags | Count |  | Follow-up actions | Count
Expired | 1 |  | Chases overdue | 3
Expiring soon | 2 |  | Chases due this week | 9
Missing | 7 |  | Chases scheduled | 8
In progress | 10 |  | Site follow-ups overdue | 2
OK | 30
Total documents | 50 |  | Filing quality check | Count
|  |  | Filed on time (Pass) | 29
Site status | Count |  | Filed late | 4
Start-up | 2 |  | On-time filing rate | 87.88%
Site Ready | 1
Recruiting | 1 |  | Payments | Count
On hold | 1 |  | Invoices unpaid | 3
|  |  | Unpaid beyond overdue limit | 1
Start-up phases (Gantt) | Count
Complete | 15
In progress | 3
Late | 1
On hold | 4
Not started | 2
Site | % documents filed | Site Ready blockers | Open issues | Overdue chases | Days vs target | Budgeted (£) | Invoiced (£) | Paid (£) | Unpaid invoices (£)
S01 Northfield General Hospital | 100% | 0 | 1 | 0 | -4 | 7500 | 7650 | 5850 | 1800
S02 Riverside University Hospital | 100% | 1 | 1 | 0 | 8 | 7500 | 5700 | 0 | 5700
S03 Ashdown Royal Infirmary | 60% | 2 | 2 | 2 |  | 7500 | 0 | 0 | 0
S04 St Wilfrid's Cancer Centre | 30% | 5 | 2 | 1 |  | 7500 | 0 | 0 | 0
S05 Castlebrook Hospital | 40% | 4 | 4 | 0 |  | 7500 | 0 | 0 | 0
Total |  | 12 | 10 | 3 |  | 37500 | 13350 | 5850 | 7500

## Settings
Settings
Report date | 2026-10-09 | Fixed so the sample looks the same whenever opened. For live use, replace with =TODAY().
Expiry warning (days) | 60 | Assumption: documents expiring within this many days are flagged 'Expiring soon'.
Study | DEMO-001 | Fictional study code.
Filing target (days) | 7 | Assumption: a received document should be filed in the eTMF within this many days.
Chase 'due soon' window (days) | 7 | Assumption: chase dates within this many days show as 'Due this week'.
Payment overdue (days) | 30 | Assumption: invoices unpaid for longer than this are highlighted.
Document status list | Site status list | Payment status list
Not started | Start-up | Not due
Requested | Site Ready | Invoice received
Received | Recruiting | Approved
Filed in eTMF | On hold | Paid

## Sites
Site ID | Site name | Principal Investigator | City | Site status | Target Site Ready date | Actual Site Ready date | Days vs target | Documents required | Documents filed | % filed | Open issues (expired / expiring / missing) | Site Ready blockers | Overdue chases
S01 | Northfield General Hospital | Investigator A | Leeds | Recruiting | 2026-08-03 | 2026-07-30 | -4 | 10 | 10 | 100% | 1 | 0 | 0
S02 | Riverside University Hospital | Investigator B | Bristol | Site Ready | 2026-09-14 | 2026-09-22 | 8 | 10 | 10 | 100% | 1 | 1 | 0
S03 | Ashdown Royal Infirmary | Investigator C | Manchester | Start-up | 2026-10-26 |  |  | 10 | 6 | 60% | 2 | 2 | 2
S04 | St Wilfrid's Cancer Centre | Investigator D | London | Start-up | 2026-11-09 |  |  | 10 | 3 | 30% | 2 | 5 | 1
S05 | Castlebrook Hospital | Investigator E | Glasgow | On hold | 2026-10-12 |  |  | 10 | 4 | 40% | 4 | 4 | 0
Site Ready blockers = documents marked 'Needed for Site Ready' that are not yet filed, plus any that are filed but expired.

## Gantt
Site start-up Gantt chart: planned phases against actual progress (fictional data)
Site ID | Phase | Planned start | Planned end | Actual start | Actual end | Status | Days vs plan | Chart start | Chart end | 2026-04-13 | 2026-04-20 | 2026-04-27 | 2026-05-04 | 2026-05-11 | 2026-05-18 | 2026-05-25 | 2026-06-01 | 2026-06-08 | 2026-06-15 | 2026-06-22 | 2026-06-29 | 2026-07-06 | 2026-07-13 | 2026-07-20 | 2026-07-27 | 2026-08-03 | 2026-08-10 | 2026-08-17 | 2026-08-24 | 2026-08-31 | 2026-09-07 | 2026-09-14 | 2026-09-21 | 2026-09-28 | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21
S01 | Feasibility and site selection | 2026-04-13 | 2026-05-11 | 2026-04-13 | 2026-05-11 | Complete | 0 | 2026-04-13 | 2026-05-11
S01 | Contract and budget (CTRA) | 2026-05-11 | 2026-07-06 | 2026-05-11 | 2026-06-29 | Complete | -7 | 2026-05-11 | 2026-06-29
S01 | Ethics and regulatory approvals | 2026-05-11 | 2026-06-29 | 2026-05-11 | 2026-06-26 | Complete | -3 | 2026-05-11 | 2026-06-26
S01 | Essential document collection | 2026-05-18 | 2026-07-20 | 2026-05-18 | 2026-07-16 | Complete | -4 | 2026-05-18 | 2026-07-16
S01 | Site initiation visit and Site Ready | 2026-07-20 | 2026-08-03 | 2026-07-20 | 2026-07-30 | Complete | -4 | 2026-07-20 | 2026-07-30
S02 | Feasibility and site selection | 2026-05-25 | 2026-06-22 | 2026-05-25 | 2026-06-22 | Complete | 0 | 2026-05-25 | 2026-06-22
S02 | Contract and budget (CTRA) | 2026-06-22 | 2026-08-17 | 2026-06-22 | 2026-08-17 | Complete | 0 | 2026-06-22 | 2026-08-17
S02 | Ethics and regulatory approvals | 2026-06-22 | 2026-08-10 | 2026-06-22 | 2026-08-14 | Complete | 4 | 2026-06-22 | 2026-08-14
S02 | Essential document collection | 2026-06-22 | 2026-08-31 | 2026-06-22 | 2026-08-28 | Complete | -3 | 2026-06-22 | 2026-08-28
S02 | Site initiation visit and Site Ready | 2026-08-31 | 2026-09-14 | 2026-09-01 | 2026-09-22 | Complete | 8 | 2026-09-01 | 2026-09-22
S03 | Feasibility and site selection | 2026-07-06 | 2026-08-03 | 2026-07-06 | 2026-08-03 | Complete | 0 | 2026-07-06 | 2026-08-03
S03 | Contract and budget (CTRA) | 2026-08-03 | 2026-09-28 | 2026-08-03 | 2026-09-19 | Complete | -9 | 2026-08-03 | 2026-09-19
S03 | Ethics and regulatory approvals | 2026-08-03 | 2026-09-21 | 2026-08-03 | 2026-09-13 | Complete | -8 | 2026-08-03 | 2026-09-13
S03 | Essential document collection | 2026-08-10 | 2026-10-12 | 2026-08-10 |  | In progress |  | 2026-08-10 | 2026-10-12
S03 | Site initiation visit and Site Ready | 2026-10-12 | 2026-10-26 |  |  | Not started |  | 2026-10-12 | 2026-10-26
S04 | Feasibility and site selection | 2026-07-20 | 2026-08-17 | 2026-07-20 | 2026-08-17 | Complete | 0 | 2026-07-20 | 2026-08-17
S04 | Contract and budget (CTRA) | 2026-08-17 | 2026-10-12 | 2026-08-17 |  | In progress |  | 2026-08-17 | 2026-10-12
S04 | Ethics and regulatory approvals | 2026-08-17 | 2026-10-05 | 2026-08-17 |  | Late | 4 | 2026-08-17 | 2026-10-05
S04 | Essential document collection | 2026-09-01 | 2026-10-26 | 2026-09-01 |  | In progress |  | 2026-09-01 | 2026-10-26
S04 | Site initiation visit and Site Ready | 2026-10-26 | 2026-11-09 |  |  | Not started |  | 2026-10-26 | 2026-11-09
S05 | Feasibility and site selection | 2026-06-22 | 2026-07-20 | 2026-06-22 | 2026-07-20 | Complete | 0 | 2026-06-22 | 2026-07-20
S05 | Contract and budget (CTRA) | 2026-07-20 | 2026-09-14 | 2026-07-20 |  | On hold |  | 2026-07-20 | 2026-09-14
S05 | Ethics and regulatory approvals | 2026-07-20 | 2026-09-07 | 2026-07-20 |  | On hold |  | 2026-07-20 | 2026-09-07
S05 | Essential document collection | 2026-07-20 | 2026-09-28 | 2026-07-20 |  | On hold |  | 2026-07-20 | 2026-09-28
S05 | Site initiation visit and Site Ready | 2026-09-28 | 2026-10-12 |  |  | On hold |  | 2026-09-28 | 2026-10-12
Key
Complete
In progress
Late
On hold
Not started
Overrun past planned end (late phases)
Week containing the report date
Each column is one week, starting on the Monday shown. The first week (blue) is typed; the rest add 7 days.
Bars are drawn by conditional formatting, not typed: a cell is coloured when its week falls between Chart start and Chart end.
Chart start and Chart end use the actual dates where they exist, otherwise the planned dates.
Status: Complete if there is an actual end date; On hold if the site is on hold; Late if the planned end has passed; In progress if started.
Green dates on the last phase of each site are pulled from the Sites tab (target and actual Site Ready date).
Days vs plan: positive = finished late or currently overdue; negative = finished early.

## Documents
Doc ID | Site ID | Document type | Needed for Site Ready? | Status | Date requested | Date received | Expiry date | Days to expiry | Flag | Owner | Notes | Date filed in eTMF | Days to file | Filing QC | Next action | Chase date | Chase status
D001 | S01 | Signed protocol signature page | Y | Filed in eTMF | 2026-05-18 | 2026-06-07 |  |  | OK | CTC |  | 2026-06-13 | 6 | Pass
D002 | S01 | Investigator CV (signed and dated) | Y | Filed in eTMF | 2026-05-21 | 2026-06-10 |  |  | OK | CTC |  | 2026-06-15 | 5 | Pass
D003 | S01 | PI GCP certificate | Y | Filed in eTMF | 2026-05-24 | 2026-06-15 | 2026-11-20 | 42 | Expiring soon | CTC | Reminder sent to PI | 2026-06-17 | 2 | Pass | Request renewed certificate before expiry | 2026-10-30 | Scheduled
D004 | S01 | REC / HRA approval letter | Y | Filed in eTMF | 2026-05-27 | 2026-06-07 |  |  | OK | CTC |  | 2026-06-13 | 6 | Pass
D005 | S01 | MHRA approval | Y | Filed in eTMF | 2026-05-30 | 2026-06-20 |  |  | OK | CTC |  | 2026-07-02 | 12 | Late
D006 | S01 | Clinical trial agreement (CTRA) fully signed | Y | Filed in eTMF | 2026-06-02 | 2026-06-13 |  |  | OK | CTC |  | 2026-06-14 | 1 | Pass
D007 | S01 | Study insurance certificate | Y | Filed in eTMF | 2026-06-05 | 2026-06-25 | 2028-01-01 | 449 | OK | CTC |  | 2026-06-26 | 1 | Pass
D008 | S01 | Delegation of duties log | Y | Filed in eTMF | 2026-06-08 | 2026-06-16 |  |  | OK | CTC |  | 2026-06-22 | 6 | Pass
D009 | S01 | Laboratory accreditation certificate | N | Filed in eTMF | 2026-06-11 | 2026-06-18 | 2027-03-15 | 157 | OK | CTC |  | 2026-06-22 | 4 | Pass
D010 | S01 | Financial disclosure form | N | Filed in eTMF | 2026-06-14 | 2026-07-04 |  |  | OK | CTC |  | 2026-07-16 | 12 | Late
D011 | S02 | Signed protocol signature page | Y | Filed in eTMF | 2026-06-22 | 2026-07-03 |  |  | OK | CTC |  | 2026-07-12 | 9 | Late
D012 | S02 | Investigator CV (signed and dated) | Y | Filed in eTMF | 2026-06-25 | 2026-07-01 |  |  | OK | CTC |  | 2026-07-07 | 6 | Pass
D013 | S02 | PI GCP certificate | Y | Filed in eTMF | 2026-06-28 | 2026-07-06 | 2027-09-09 | 335 | OK | CTC |  | 2026-07-06 | 0 | Pass
D014 | S02 | REC / HRA approval letter | Y | Filed in eTMF | 2026-07-01 | 2026-07-13 |  |  | OK | CTC |  | 2026-07-15 | 2 | Pass
D015 | S02 | MHRA approval | Y | Filed in eTMF | 2026-07-04 | 2026-07-10 |  |  | OK | CTC |  | 2026-07-15 | 5 | Pass
D016 | S02 | Clinical trial agreement (CTRA) fully signed | Y | Filed in eTMF | 2026-07-07 | 2026-07-23 |  |  | OK | CTC |  | 2026-07-28 | 5 | Pass
D017 | S02 | Study insurance certificate | Y | Filed in eTMF | 2026-07-10 | 2026-08-03 | 2026-09-30 | -9 | Expired | CTC | Renewal requested from site 01-Oct | 2026-08-09 | 6 | Pass | Obtain renewed certificate (urgent) | 2026-10-12 | Due this week
D018 | S02 | Delegation of duties log | Y | Filed in eTMF | 2026-07-13 | 2026-07-26 |  |  | OK | CTC |  | 2026-08-07 | 12 | Late
D019 | S02 | Laboratory accreditation certificate | N | Filed in eTMF | 2026-07-16 | 2026-07-31 | 2028-05-16 | 585 | OK | CTC |  | 2026-07-31 | 0 | Pass
D020 | S02 | Financial disclosure form | N | Filed in eTMF | 2026-07-19 | 2026-07-27 |  |  | OK | CTC |  | 2026-08-01 | 5 | Pass
D021 | S03 | Signed protocol signature page | Y | Filed in eTMF | 2026-08-10 | 2026-08-24 |  |  | OK | CTC |  | 2026-08-28 | 4 | Pass
D022 | S03 | Investigator CV (signed and dated) | Y | Filed in eTMF | 2026-08-13 | 2026-09-05 |  |  | OK | CTC |  | 2026-09-06 | 1 | Pass
D023 | S03 | PI GCP certificate | Y | Filed in eTMF | 2026-08-16 | 2026-08-30 | 2026-10-28 | 19 | Expiring soon | CTC | PI booked on refresher course | 2026-09-01 | 2 | Pass | Request renewed certificate before expiry | 2026-10-07 | Overdue
D024 | S03 | REC / HRA approval letter | Y | Filed in eTMF | 2026-08-19 | 2026-09-10 |  |  | OK | CTC |  | 2026-09-13 | 3 | Pass
D025 | S03 | MHRA approval | Y | Filed in eTMF | 2026-08-22 | 2026-08-28 |  |  | OK | CTC |  | 2026-08-29 | 1 | Pass
D026 | S03 | Clinical trial agreement (CTRA) fully signed | Y | Filed in eTMF | 2026-08-25 | 2026-09-18 |  |  | OK | CTC |  | 2026-09-19 | 1 | Pass
D027 | S03 | Study insurance certificate | Y | Received | 2026-08-28 | 2026-09-15 | 2027-12-14 | 431 | In progress | CTC |  |  |  |  | Quality check and file in eTMF | 2026-10-11 | Due this week
D028 | S03 | Delegation of duties log | Y | Received | 2026-08-31 | 2026-09-18 |  |  | In progress | CTC |  |  |  |  | Quality check and file in eTMF | 2026-10-09 | Due this week
D029 | S03 | Laboratory accreditation certificate | N | Requested | 2026-09-03 |  |  |  | In progress | CTC |  |  |  |  | Chase site for outstanding document | 2026-10-03 | Overdue
D030 | S03 | Financial disclosure form | N | Not started |  |  |  |  | Missing | CTC |  |  |  |  | Send document request to site | 2026-10-12 | Due this week
D031 | S04 | Signed protocol signature page | Y | Filed in eTMF | 2026-09-01 | 2026-09-07 |  |  | OK | CTC |  | 2026-09-09 | 2 | Pass
D032 | S04 | Investigator CV (signed and dated) | Y | Filed in eTMF | 2026-09-04 | 2026-09-16 |  |  | OK | CTC |  | 2026-09-16 | 0 | Pass
D033 | S04 | PI GCP certificate | Y | Filed in eTMF | 2026-09-07 | 2026-09-28 | 2028-05-12 | 581 | OK | CTC |  | 2026-10-02 | 4 | Pass
D034 | S04 | REC / HRA approval letter | Y | Received | 2026-09-10 | 2026-09-29 |  |  | In progress | CTC |  |  |  |  | Quality check and file in eTMF | 2026-10-09 | Due this week
D035 | S04 | MHRA approval | Y | Received | 2026-09-13 | 2026-10-07 |  |  | In progress | CTC |  |  |  |  | Quality check and file in eTMF | 2026-10-10 | Due this week
D036 | S04 | Clinical trial agreement (CTRA) fully signed | Y | Requested | 2026-09-16 |  |  |  | In progress | CTC | With site R&D office for signature |  |  |  | Chase site for outstanding document | 2026-10-07 | Overdue
D037 | S04 | Study insurance certificate | Y | Requested | 2026-09-19 |  |  |  | In progress | CTC |  |  |  |  | Chase site for outstanding document | 2026-10-12 | Due this week
D038 | S04 | Delegation of duties log | Y | Requested | 2026-09-22 |  |  |  | In progress | CTC |  |  |  |  | Chase site for outstanding document | 2026-10-14 | Due this week
D039 | S04 | Laboratory accreditation certificate | N | Not started |  |  |  |  | Missing | CTC |  |  |  |  | Send document request to site | 2026-10-16 | Due this week
D040 | S04 | Financial disclosure form | N | Not started |  |  |  |  | Missing | CTC |  |  |  |  | Send document request to site | 2026-10-17 | Scheduled
D041 | S05 | Signed protocol signature page | Y | Filed in eTMF | 2026-07-20 | 2026-07-28 |  |  | OK | CTC |  | 2026-07-31 | 3 | Pass
D042 | S05 | Investigator CV (signed and dated) | Y | Filed in eTMF | 2026-07-23 | 2026-08-08 |  |  | OK | CTC |  | 2026-08-08 | 0 | Pass
D043 | S05 | PI GCP certificate | Y | Filed in eTMF | 2026-07-26 | 2026-08-14 | 2027-11-17 | 404 | OK | CTC |  | 2026-08-15 | 1 | Pass
D044 | S05 | REC / HRA approval letter | Y | Filed in eTMF | 2026-07-29 | 2026-08-11 |  |  | OK | CTC |  | 2026-08-12 | 1 | Pass
D045 | S05 | MHRA approval | Y | Received | 2026-08-01 | 2026-08-07 |  |  | In progress | CTC |  |  |  |  | Review when site hold is lifted | 2026-11-02 | Scheduled
D046 | S05 | Clinical trial agreement (CTRA) fully signed | Y | Requested | 2026-08-04 |  |  |  | In progress | CTC |  |  |  |  | Review when site hold is lifted | 2026-11-02 | Scheduled
D047 | S05 | Study insurance certificate | Y | Not started |  |  |  |  | Missing | CTC | Site on hold pending capacity review |  |  |  | Review when site hold is lifted | 2026-11-02 | Scheduled
D048 | S05 | Delegation of duties log | Y | Not started |  |  |  |  | Missing | CTC |  |  |  |  | Review when site hold is lifted | 2026-11-02 | Scheduled
D049 | S05 | Laboratory accreditation certificate | N | Not started |  |  |  |  | Missing | CTC |  |  |  |  | Review when site hold is lifted | 2026-11-02 | Scheduled
D050 | S05 | Financial disclosure form | N | Not started |  |  |  |  | Missing | CTC |  |  |  |  | Review when site hold is lifted | 2026-11-02 | Scheduled

## Payments
Payment ID | Site ID | Milestone | Budgeted (£) | Invoice received | Invoiced (£) | Status | Date paid | Variance (£) | Days outstanding
P001 | S01 | Site set-up fee | 4500 | 2026-08-05 | 4500 | Paid | 2026-08-28 | 0
P002 | S01 | First patient enrolled | 1800 | 2026-09-18 | 1800 | Approved |  | 0 | 21
P003 | S01 | Pharmacy set-up fee | 1200 | 2026-08-12 | 1350 | Paid | 2026-09-04 | 150
P004 | S02 | Site set-up fee | 4500 | 2026-09-25 | 4500 | Invoice received |  | 0 | 14
P005 | S02 | First patient enrolled | 1800 |  |  | Not due
P006 | S02 | Pharmacy set-up fee | 1200 | 2026-08-20 | 1200 | Invoice received |  | 0 | 50
P007 | S03 | Site set-up fee | 4500 |  |  | Not due
P008 | S03 | First patient enrolled | 1800 |  |  | Not due
P009 | S03 | Pharmacy set-up fee | 1200 |  |  | Not due
P010 | S04 | Site set-up fee | 4500 |  |  | Not due
P011 | S04 | First patient enrolled | 1800 |  |  | Not due
P012 | S04 | Pharmacy set-up fee | 1200 |  |  | Not due
P013 | S05 | Site set-up fee | 4500 |  |  | Not due
P014 | S05 | First patient enrolled | 1800 |  |  | Not due
P015 | S05 | Pharmacy set-up fee | 1200 |  |  | Not due
Invoices unpaid for longer than the 'Payment overdue' setting are highlighted. Positive variance = invoiced above budget.

## Contact Log
Contact ID | Date | Site ID | Contact (role) | Method | Subject | Outcome | Follow-up due | Follow-up done? (Y/N) | Follow-up status
C001 | 2026-09-21 | S02 | Research nurse | Email | Insurance certificate expiring 30-Sep | Site to request renewal from their R&D office | 2026-09-28 | Y | Done
C002 | 2026-10-01 | S02 | R&D office | Phone | Insurance renewal not yet received | Renewal in progress; certificate promised by 12-Oct | 2026-10-12 | N | Open
C003 | 2026-09-24 | S03 | Principal Investigator | Email | GCP certificate expires 28-Oct | PI booked on refresher course | 2026-10-07 | N | Overdue
C004 | 2026-09-29 | S04 | R&D office | Email | CTRA signature status | Contract with site legal team; update expected in one week | 2026-10-06 | N | Overdue
C005 | 2026-10-02 | S04 | Site coordinator | Phone | Outstanding start-up documents | Site to send insurance certificate and delegation log | 2026-10-14 | N | Open
C006 | 2026-09-15 | S05 | Principal Investigator | Meeting | Site capacity and hold decision | Site placed on hold; review in November | 2026-11-02 | N | Open
C007 | 2026-09-10 | S01 | Pharmacy lead | Email | Pharmacy set-up invoice above budget | Extra dispensing visit confirmed; variance approved by CRM | 2026-09-17 | Y | Done
C008 | 2026-10-05 | S02 | Finance contact | Email | Pharmacy invoice unpaid since 20-Aug | Escalated to finance for payment run | 2026-10-09 | N | Open
C009 | 2026-10-06 | S01 | Principal Investigator | Email | GCP certificate expires 20-Nov | Reminder sent; PI acknowledged | 2026-10-30 | N | Open
C010 | 2026-10-07 | S03 | Site coordinator | Phone | Documents received awaiting filing | Confirmed final versions; ready for QC | 2026-10-10 | N | Open

## Change Log
Change ID | Date | Tab | Record ID | Field | Old value | New value | Changed by | Reason
L001 | 2026-07-30 | Sites | S01 | Actual Site Ready date | (blank) | 30-Jul-2026 | CTC | Site initiation completed; confirmed by CRA
L002 | 2026-09-04 | Payments | P003 | Status | Approved | Paid | CTC | Payment confirmed by finance; variance of £150 approved by CRM
L003 | 2026-09-15 | Sites | S05 | Site status | Start-up | On hold | CTC | Site capacity review; decision recorded in Contact Log C006
L004 | 2026-09-22 | Sites | S02 | Actual Site Ready date | (blank) | 22-Sep-2026 | CTC | Site Ready confirmed 8 days after target; pharmacy set-up delayed
L005 | 2026-09-22 | Sites | S02 | Site status | Start-up | Site Ready | CTC | All documents needed for Site Ready filed
L006 | 2026-09-25 | Settings | - | Expiry warning (days) | 30 | 60 | CTC | Agreed with COM: 30 days too short to obtain renewals
L007 | 2026-10-01 | Documents | D017 | Notes | (blank) | Renewal requested from site 01-Oct | CTC | Insurance expired 30-Sep; renewal chased
L008 | 2026-10-07 | Documents | D027 | Status | Requested | Received | CTC | Document received from site by email
Rule: never overwrite a status, date or amount without adding a row here. Entries are added, never deleted.